## Corporate Risk Register
Risk Register: Llais Corporate Risk Register (Last reviewed Agreed by Board November 2023)
Category | Risk No. | Risk Owner | Risk Description | Inherent Impact | Inherent Likelihood | Inherent rating | Risk Control (what is actually happening) | Residual Impact | Residual likelihood | Residual rating | Change to rating since last discussed | Further actions underway/required | Tolerable Impact | tolerable likelihood | tolerable rating | Link to Risk Appetite | Sources of assurance | Commentary
Organisational Delivery | CR1 | Chris Davies (HR) | People and skills - unable to acquire or retain expertise and skills mix in key areas, leading to an inability to carry out some functions. New starters need time to adapt to new ways of working which may impact efficiency and delivery. | 4 | 4 | 16 | 1. New roles and skills required for first 12 months of operations have been identified and majority recruited to. 2. Transfer of staff from CHC complete 3. Fortnightly communications with staff is taking place 4. Scoping exercise taking place to identify additional support required at a regional level 5. Guidance documents to support staff have been developed 6. Recruitment has taken place in key areas to support staff e.g. operations, corporate services, people and IT intial OD work completed 7. Agency appointed to support a range of activities, including: organisational development, digital infrastructure, equity diversity and inclusion and project support. 8. Horizon scanning for possible recruitment pressures | 3 | 2 | 6 |  | 1. further OD work underway 2. schedule remaining recruitment 3. Tim Arwain to share/explain purpose and key attributes of roles in each area's structure (to avoid duplication/spot gaps) 4. Consider 'job sharing' areas of knowledge/work 5. further develop succession planning arrangements 6. further develop exit interview process to capture knowledge implemented 7. Review L&D budget 8. Further develop training induction document, processes and plans 9. Identify areas where our people may be struggling and run informal drop in sessions over teams so that our people can learn and ask questions. e.g. new IT systems | 2 | 3 | 6 | RA5 - eager to innovate RA8 - eager to help our people develop and do things differently | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review Further Assurance: Internal Audit
| CR2 | Chris Davies (HR) | Organisational culture - unable to establish common culture early on may have longer term impacts. | 3 | 3 | 9 | 1. An assessment of CHC culture was carried out 2. discussions have begun at Board level 3. Feedback from staff on key policies and procedures has been collected and implemented | 3 | 3 | 9 |  | 1. Assess findings from CHC culture work 2. Develop culture statement and strategy 3. Engagement sessions with our people 4. Determine how we will measure culture and report 5. Ensure policies and procedure reflect desired culture | 1 | 2 | 2 | RA7 - averse to decisions that could impact welfare of our people, our priority is to build trust | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review Further Assurance: Internal Audit
| CR3 | Katie Blackburn (RD) | Volunteers - some former CHC members are finding the transition to Llais volunteer approach and new ways of working challenging. This could lead to gaps in service delivery. | 3 | 2 | 6 | 1. Process for recruiting volunteers is in place 2. 112 volunteers successfully transferred from CHCs and more appointed since 1 April. 3. security check criteria system is in place and being implemented. 4. some training for volunteers in place - interim training programme. 5. recruited approx 20 new volunteers - individuals eager and willing to support Llais as much as possible. 6. Staff ensuring they are available for engagement events for additional support. | 3 | 2 | 6 |  | 1. e-learning modules and further training being developed. 2. contract with synthesia (AI software) to deliver training - in the pipeline | 1 | 2 | 2 | RA5 - eager for innovation. We are a new ambitious organisation wanting to make real change for the people of Wales. | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review Further Assurance: Internal Audit
| CR4 | Angela Mutlow (SD-OCP) | Unexpected/Uncertainty of demand - unplanned demand from the public or stakeholders exceeds capacity, leading to resource pressures or failure to deliver service. Addition of social care brings with it many unknowns, service demand could impact delivery of Llais functions | 4 | 4 | 16 | 1. 2x monthly Tîm Arwain meetings to respond to emerging problems and clear governance arrangements to escalate issues; 2. Planning our work to align with key events 3. Recruitment planned and taking place 4. Reserve lists created during recruitment process 5. Work closely with Welsh Government and NWSSP for advice and support 6. Utilise agency staff and WG and NWSSP resource to assist with establishment to allow Llais staff to focus on service delivery 7. Engagement and communications with social care providers to determine service need 8. Additional complaints advocates appointed | 3 | 3 | 9 |  | 1. Recruitment & training of staff ensure flexibility of teams to respond to demand 2. Ensure job descriptions have sufficient flexibility so that job holder can be re-deployed (implement to all new roles - consider changes required to existing roles~) 3. Consider possible job/knowledge sharing to help meet demand 5. Monitor demand and deploy resources as necessary Develop performance measures and review data to identify patterns and develop forecast 6. Develop strategy / risk identification and management plan 4. Agree key priority work areas 7. Business continuity plans developed for operational issues 9. Ensure organisational design has flexibility in the deployment of resources to enable response to changes - looking at cross functional working solutions (e.g. utilising non-operational staff to support with operational issues as required). In particular develop a holistic approach to managing issues across Llais. Tîm Arwain review of roles and responsibilities. 10. Work closely with WG Policy leads to discuss any legislative impact or patterns 11. Consider building capacity for annual pressures e.g. budget changes or annual plan and report 12. Work closely with health and social care providers to identify upcoming service change and emerging risks and trends 13. Establish working groups within Llais and utilise to assist with solutions to emerging problems 14. Consider possible stakeholder engagement groups to be established to identify risks and emerging issues early 15.Develop our people knowledge and understanding through awareness training session Sufficient training for complaints advocates staff and other staff to build capability in this area | 1 | 2 | 2 | RA6 - averse to decisions that adversely affect how partners & public see us | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review Further assurance: Internal Audit
| CR5 | Angela Mutlow (SD-OCP) | Accessibility - any changes to Llais location could impact accessibility for our people and the public and impact on service delivery. | 4 | 4 | 16 | 1. Leases for former CHC buildings were transferred to Llais and Board agreed leases would be extended to allow time for Llais to develop location strategy. 2. Ability to work remotely should limit impact of any move 3. Cost for leases is covered in the agreed budget with WG 4. Consideration being given to using public hubs. 5. actively seeking assurance that none of our locations are affected by the Reinforced autoclaved aerated concrete (RAAC) risks | 2 | 2 | 4 |  | 1.Develop accessibility strategy 2. Develop location strategy. 3. ongoing discussions to resolve arrangements for all locations | 2 | 1 | 2 | RA6 - averse to decisions that adversely affect how partners & public see us - priority is to build trust & establish positive relationships | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review
Operational Support | CR6 | Angela Mutlow (SD-OCP) | IT implementation - delay in implementing IT systems inhibiting staff to carry out their roles effectively and efficiently and impacting staff morale. | 5 | 4 | 20 | 1. Testing is complete with plans for IT issues to be resolved 2. Communications to staff on IT plans for Cimla office only 3. Support in place for staff - Centerprise as well internal support - for Cimla office only 4. All staff have moved over with the exception of Cimla 5. Datix has been adapted so that it can be used with Social care 6. Network switch support proposal being put together to ensure engineer support is available when needed. 7. staff resourcing and training for CRM project planned. | 3 | 3 | 9 |  | 1. Networking issues may cause delays with the delivery of end user system 2. Create CRM system by end Feb 2024 | 1 | 2 | 2 | RA7 - averse to decisions that could impact welfare of our people, our priority is to build trust | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review Further Assurance: Internal Audit
| CR7 | Angela Mutlow (SD-OCP) | Finance - unplanned expenditure incurred due to uncertainty around demand, weak approval systems or fraud, leading to costs exceeding budget. | 5 | 5 | 25 | 1. Budget monitoring and management accounts ensure that total spending is controlled and forecast through to year-end 2. Restricted access levels to finance system for most staff 3. Schedule of internal delegations ensures that major spending is approved at correct levels 4. Standing Financial Instructions agreed and in place 5. Discussions with WG on budget for 2023/24 concluded 6. Financial control procedures being monitored and update in response to learning 7. Finance Manager appointed. | 4 | 3 | 12 |  | 1. More Financial Control Procedures being developed 2. Continue discussions with WG on budget pressures 3. Further review of systems to minimise opportunities for internal fraud 4. Develop and implement training for staff on finance related policies and controls 5. appointment of Director of Finance and Governance underway | 1 | 1 | 1 | RA1 - averse to financial loss or impact | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review ARAC review Further Assurance: Internal Audit External Audit
| CR8 | Keith Chung (IT) | Systems failure - Loss of digital infrastructure and systems, including physical network connectivity, key applications such Office 365, which includes e-mails SharePoint and Customer Relationship Management (CRM)/Datix. This would lead to Llais operations being unable to function, halting or delaying deliverable services. | 5 | 4 | 20 | 1. IT Health Check of the new IT systems to ensure they remain robust - completed 2. Changes made to Microsoft Entra system to ensure the recommended changew from the IT Health Check are implemented. 2. Full security risk assessment being completed on systems - and making changed with accordance to Audit Wales recommendations. 3. Monthly Security and Compliance reports are checked to ensure any devices connected to the network are compliant with systems policies. These include making sure devices have checked in within a 30 day period to ensure any network changed and software updates are applied to devices. 4. All amendments made based on recommendations from IT Health Check. | 3 | 3 | 9 |  | 1. develop business continuity plan to covers IT, operations, and locations, maintain. 2. Review and update the “Disaster Recovery Plan” on an ongoing basis. 3. Monthly reviews of applications updates 4. Ensure staff are trained on use of Llais systems, CRM and Office 365 suite including CRM. 5. Ensure new staff know the correct procedure to raise IT support calls and know who to contact with queries. 6. Monthly checks of the network and infrastructure provided for by 5i, Centerprise’s 3rd party network support vendor, this includes monthly checks for network switch firmware updates. | 1 | 1 | 1 | RA6 - averse to decisions that adversely affect how partners & public see us RA9 - averse when it comes to safety of information and data | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review ARAC review Further Assurance: Internal Audit External validation/accreditation
| CR9 | Keith Chung (IT) | Cyber Security – digital systems unavailable through hacking and other forms of cyber-attack, due to weaknesses or vulnerability in security, could lead to key operations not being available potential loss of data, delay or extended recovery time, loss of credibility with the public and stake holders, Llais unable to function and comply with new governance framework. | 5 | 4 | 20 | 1. Monthly reviewing of security reports from Entra (Our online cloud-based network domain) for Microsoft security recommendations and updates. 2. Only allowing compliant devices to connect to the Llais network. For devices to be compliant they will need to meet the following rules. a. Devices must connect to the network and “check in” at least once in a 30-day period. b. Must be running the minimum recommended Microsoft Version of windows with the latest security patches/update applied. c. Must be a Llais registered work device. 3. Device compliance reviews of applications. 4. Ensure staff receive Cybersecurity training on an annual basis. 5. Ensure staff read and understand the Llais IT security policy, this will be included in the new staff induction pack. | 3 | 3 | 9 |  | 1. Monthly IT Security reviews of the system via the Microsoft reporting system. 2. Deployment of Microsoft recommended security updates and patches, as noted in the Monthly security review. 3. Ensuring device compliance for all Llais devices. Non-compliant devices will not be able to connect to the work and access the Office 365 Suite or SharePoint. 4. Review applications not covered by the Microsoft reporting system and ensure that security updates have been deployed to end user devices. 5. Ensure that cybersecurity training is carried out at least on an annual basis. 6. Create a quarterly security report or newsletter to all staff to keep them informed of potential security threats. | 1 | 1 | 1 | RA6 - averse to decisions that adversely affect how partners & public see us RA9 - averse when it comes to safety of information and data | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review ARAC review Further Assurance: Internal Audit External validation/accreditation
Strategic Impact | CR10 | Angela Mutlow (SD-OCP) | National approach - unable to embed a national approach, leading to a lack of understanding, poorly designed systems, and inefficiencies in systems. | 4 | 4 | 16 | 1. Clear communication with staff 2. Corporate documents explaining governance structures, delegations, processes and procedures 3. Staff and volunteer engagement sessions and regular updates for our people 4. Key messages developed for briefing and stakeholder engagement 5. Working with partners to communicate the national approach 6. Working with third party to design a CRM system that is fit for purpose | 3 | 2 | 6 |  | 1. Ongoing timely communications to staff, volunteers and public on any significant changes if needed | 2 | 3 | 6 | RA5 - eager to innovate - we are a new ambitious organisation | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review Further Assurance: Internal Audit External Audit
| CR11 | Ben Eaton (SD-OSC) | Scope and remit - Internal knowledge, understanding and lack of clarity of Llais's remit may lead to gaps in service delivery or to Llais operating outside of it's remit. Lack of external knowledge may lead to Llais being asked to take forward matters outside of our remit | 4 | 4 | 16 | 1. working closely with WG policy leads 2. Legals service support in place 3. Internal knowledge and understanding is growing by the day | 3 | 2 | 6 |  | 1. develop guidance to sit alongside legislation to explain things in practical terms and provide clarity on any grey areas 2. arrange training sessions for our people - seek feedback on areas that are unclear 3. Where uncertainty arises - escalate to WG 4. TA carry out exercise to identify gaps - ongoing piece of work | 2 | 1 | 2 | RA3 - averse to decisions that may compromise compliance with statutory, regulatory or policy requirements | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review
| CR12 | Ben Eaton (SD-OSC) | Public and stakeholder expectations - public expectations regarding quality of service cannot be met, leading to reputational impact - criticism, gaps in service and lack of confidence and the need for further change. | 4 | 4 | 16 | 1. Partnership working, engagement with public, partners and stakeholders and use of feedback and surveys to understand expectations 2. Using our peoples knowledge and expertise to inform policies and guidance through feedback and surveys 3. Systems and processes in place to comply with GDPR requirements, and to identify, communicate and resolve personal data breaches | 3 | 3 | 9 |  | 1. Regular review of guidance. Identifying gaps and improvements 2. Develop communications strategy aims to manage expectations around delivery, and ensure that Llais is visible and transparent in its achievements, while also managing bad news 3. Use public insight and feedback to shape and prioritise changes 4. Honest and open communications with the public about changes we are making, changes we won't be making, and things we have learned 5. Llais collaboration with partners to ensure guidance and communications is fit for purpose and is a consistent across organisations 6. Develop and implement quality control and checks around communications. | 1 | 2 | 2 | RA6 - averse to decisions that adversely affect how partners & public see us - priority is to build trust & establish positive relationships | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review
| CR13 | Alyson Thomas | Partnership relations - difficulty implementing changes to pre-existing relationships with key stakeholders, difficulty to create new relationships with key stakeholders could lead to misunderstanding of Llais's purpose and prevent Llais from successfully delivering its functions, impacting Llais reputation and ability to gain confidence as a trusted and impactful organisation. | 3 | 3 | 9 | 1. Draft collaboration arrangements developed to kick off discussions with partners 2. Engaging with stakeholders to strengthen relationships - at operational level and Board level 3. Engagement with key stakeholders on our functions 4. Promotion of Llais role and functions 5. HIW MoU agreed | 2 | 2 | 4 |  | 1. Agree remaining MoU's and SLA's 2. Regularly review partnership arrangements to ensure they are working effectively 3. Develop trust and openness in our partnerships through open and frequent communications 4. Develop a stakeholder engagement plan to map out and ensure Llais's key partnerships have the attention they deserve and need, from the right people 5. continued development of who we are and what we do | 2 | 2 | 4 | RA5 - eager to innovate - we are a new ambitious organisation RA6 - averse to decisions that adversely affect how partners & public see us - priority is to build trust & establish positive relationships | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review
| CR14 | Angela Mutlow (SD-OCP) | Statutory obligations - Uncertainty of scope and extent of statutory obligations (known and unknown) leading to failure to meet wider legal and regulatory obligations and/or fines or losses. | 4 | 4 | 16 | 1. Legal support in place to provide support on complying with statutory requirements 2. Close working with Welsh Government on applying existing and planned legislation 3. Some policies and guidance in place on statutory obligations - shared with staff for awareness and feedback 4. Regular communication with WG to remain aware of any emerging of future statutory requirements Llais need to comply with | 3 | 3 | 9 |  | 1. Develop further guidance for staff on statutory obligations 2. Develop and implement training for staff on legal and regulatory guidance 3. Statutory guidance on engagement and consultation on changes to health services near being finalised 4. Considering undertaking review policies and procedures. | 1 | 1 | 1 | RA3 - averse to decisions that may compromise compliance with statutory, regulatory or policy requirements | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review ARAC review Further Assurance: Internal Audit External Audit
| CR15 | Angela Mutlow (SD-OCP) | Key partnership and service provider arrangements - Failure to agree service provision (including service standards) levels with Velindre, NWSSP and DHCW early on could lead to gaps or inappropriate services provided to Llais and have a longer term impact on the relationships with these key service providers | 4 | 4 | 16 | 1. Ongoing dialogue with service providers to resolve outstanding queries around SLA's 2. Working with Llais lawyers to address outstanding queries 3. HIW MoU agreed. | 4 | 3 | 12 |  | 1. Agree remaining SLA's and MoU's (letter with DHCW agreed ad signed - it outlines the services they provide us now and cost) 2. communicate SLA's and MoU's internally to ensure the requirements are met 3. align policies and procedures with SLA's | 1 | 1 | 1 | RA1 - averse risk appetite to any financial loss or impact. Value for money is a key objective RA3 - averse to decisions that may compromise compliance with statutory, regulatory or policy requirements RA6 - cautious for decisions that could adversely affect how our partners and the public see us. Our priority is to build trust and establish positive relationships. | Existing Assurance: Control framework Management framework Control self assessment Assurance and reporting to TA Risk and compliance review Feedback from stakeholders Board review ARAC review Legal services advice and guidance Further Assurance: Internal Audit
This document contains the Llais Risk Register. Please seek authorisation from the Governance Manager and/or Strategic Director of Operations and Corporate Services before publishing this document or sharing it outside of Llais.
Note on D7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we need to add something specific in the actions section to reflect our checks following the RAAC risks?

## Risk Scoring
Risk scoring
Impact
Probability | Score | Likelihood
Low | 1 | Minimal loss, delay, inconvenience or interruption. Can be easily and quickly remedied
Low/medium | 2 | Minor loss, delay, inconvenience or interruption. Short to medium term effect
Medium | 3 | Significant waste of time and resources. Impact on operational efficiency, output and quality. Medium term which may be expensive to recover
Medium/high | 4 | Major impact on costs and objectives. Serious impact on output and/or quality and reputation. Medium to longterm effect and expensive to recover
High | 5 | Critical impact on the achievement of objectives and overall performance. Huge impact on costs and/or reputation. Very difficult and possibly long term to recover.
Likelihood
Probability | Score | Likelihood
Low | 1 | Rare (0-5%). The risk will materialise only in exceptional circumstances
Low/medium | 2 | Unlikely (5-25%). The risk will probably not materialise
Medium | 3 | Possible (25-75%). The risk might materialise at some time
Medium/high | 4 | Likely (75-95%). The risk will probably materialise at least once
High | 5 | Almost certain (>95%). The risk will materialise in most circumstances

## Risk appetite
Llais Risk Appetite
Finance/VfM |  | RA1 | We have an averse risk appetite to any financial loss or impact. Value for money is a key objective.
|  | RA2 | We have an eager risk appetite to invest where there is benefit to the establishment of Llais systems, functions and services
Governance |  | RA3 | We have an averse risk appetite for decisions that may compromise compliance with statutory, regulatory or policy requirements particularly during our establishment phase
|  | RA4 | We have an eager risk appetite to our internal governance controls. We want our internal controls to reflect our culture. We want our people to feel empowered to make decisions and not feel like they are restricted by red tape.
Operational and policy delivery |  | RA5 | We have an eager risk appetite to innovation. We are a new ambitious organisation wanting to make real change for the people of Wales.
Reputational |  | RA6 | We have a cautious risk appetite for decisions that could adversely affect how our partners and the public see us. Our priority is to build trust and establish positive relationships.
Our people |  | RA7 | We have an averse risk appetite for decisions that could have a negative impact on the welfare of our people. Our priority is to build trust with our staff and volunteers.
|  | RA8 | We have an eager risk appetite to helping our people develop and to doing things differently and for the better. We want to provide our people with opportunities to share ideas and suggest new ways of working.
Information and data |  | RA9 | We have an averse risk appetite when it comes to the safety of the information and data we hold about our people and the public and the damage that could be caused by the disclosure of that information.
|  | RA10 | We have an eager approach when it comes to sharing information that will improve joint working with our strategic partners, but only where the aim is to improve services for the people of Wales.