## Action Log
2024/2025 Llais Board Action Items Tracker
Action Reference | Goals & Action Items | Region Responsible | Person(s) Responsible | Start Date | Due Date | Status | % completion of each action item | Update / Notes
A24-12-01 | Annual report and accounts: The board approved the annual report and accounts and it was agreed that they would be submitted to the Auditor General and Welsh Ministers. The documentation would also be published on the Llais website. | National Team | Alyson Thomas | 2024-12-01 | 2024-12-01 | Complete | 100% | The documentation was submitted to the Auditor General and Welsh Ministers on the 18 December 2024. The annual report and accounts have also been uploaded to the Llais website.
A24-09-01 | Health & Social Care Services Presentation: Presentation to be circulated to all board Llais members. | National Team | Katie Blackburn | 2024-09-01 | 2024-10-01 | Complete | 100%
A24-09-02 | Finance update/Pay Award: Meeting required with the Deputy Medical Officer at Welsh Government regarding the uplift for staff pay award and agenda for change. A meeting to be arranged with the Board via teams once clarity has been obtained. | National Team | Alyson Thomas | 2024-09-01 | 2024-09-01 | Complete | 100%
A24-09-03 | Workforce Dashboard: It was agreed that the dashboard was to be adapted to reflect appraisal input and detailed report on leavers. | National Team | Joanne Bolton/Chris Davies | 2024-09-01 | 2024-12-01 | Complete | 100%
A24-09-04 | Corporate Risk Dashboard: Enhanced Dashboard to be produced through the OKR system. | National Team | Ben Eaton/Richard Bevan | 2024-09-01 | 2025-03-01 | In Progress | 50% | Discussions have taken place regarding generating a risk dashboard from the OKR system. A new dashboard will be produced in line with the finalisation of the new risk management strategy, which will be presented to the Board in March 2025.
A24-09-05 | Forward Look/Workplan: The forward look and board workplan to be reviewed by the Executive Team and the board is to receive an updated version. | National Team | Executive Team | 2024-09-01 | 2024-12-01 | Complete | 100% | Update provided at the October 2024 Board Development Session.
A24-09-06 | Forward Look/Workplan: Board to receive the updated version of the Equality, Diversity and Inclusion and SEP progress and plans for the remainder of the 2024 to be presented at the board briefing and development session in October 2024. | National Team | Ben Eaton/Mwoyo Makuto/Charysse Harper | 2024-09-01 | 2024-10-01 | Complete | 100% | Update provided at the October 2024 Board Development Session.
A24-07-01 | Report from Chair on Partnership Working: response to the Welsh Government consultation on Regional Partnership Boards to confirm Llais's involvement with partners to highlight significant issues in health and social care and seek integrated approaches. | National Team | Alyson Thomas | 2024-07-01 | 2024-09-01 | Complete | 100% | Llais involvement in Regional Partnership Boards has been formalised and Llais representatives attend meetings with speaking rights
A24-01-02 | Workforce Metrics: The National Team to provide further information on the diversity of applicants applying for roles within Llais. | National Team | Joanne Bolton/Chris Davies | 2024-01-01 | 2024-07-01 | In Progress | 75% | Capacity challenges have delayed completion on this matter. Programme to review recruitment arrangements incorporates action relating to collection of more meaningful diversity data

## Closed Actions
2024/2025 Llais Board Closed Actions Tracker
Action Reference | Action Items | Region Responsible | Person(s) Responsible | Start Date | Due Date | Status | % completion of each action item | Notes
A24-07-02 | Standing Orders: It was agreed that the standing orders would be posted to the Llais website and that awareness raising with staff would be undertaken to develop understanding and compliance. | Governance | Richard Bevan | 2024-07-01 | 2024-09-01 | Complete | 100% | New Governance pages have been developed on the intranet and all Governance documentation will be available on these pages. The Interim Board Secretary has raised awareness with Tim Arwain and offered development sessions for regions and functions.
A24-07-03 | Board Schedule of Matters Reserved: It was agreed that the schedule of matters reserved would be posted to the Llais website. | Governance | Richard Bevan | 2024-07-01 | 2024-09-01 | Complete | 100% | New Governance pages have been developed on the intranet and all Governance documentation will be available on these pages. The Interim Board Secretary has raised awareness with Tim Arwain and offered development sessions for regions and functions.
A23-05-02 | IT Systems: The Board noted the expected timeline with the establishment of the Llais IT systems and asked that this was kept under review. |  | Angela Mutlow | 2023-05-01 | 2024-01-01 | Complete | 100%
A23-05-06 | Produce summary and easy read version of the ‘Our first 100 days’ report for publication. |  | Ben Eaton | 2023-05-01 | 2024-01-01 | Complete | 100%
A24-04-03 | Corporate Risk: The Board agreed that a new dashboard style Corporate Risk Report/Register would be developed and presented at the July 2024 Board. | Governance | Richard Bevan | 2024-04-01 | 2024-07-01 | Complete | 100% | In interim dashboard was presented at the July Board and further work is underway to develop a finalised dashboard linked to the OKR system.
A24-04-02 | Public Statement: The Chief Executive, as part of the communications arrangements for Llais, would publish a regular statement for the public to highlight the work of Llais and its key achievements and impacts. | National Team | Alyson Thomas | 2024-04-01 | 2024-07-01 | Complete | 100% | The first public statement is due to be published in October 2024. Routine monthly reports are being issued.
A23-03-13 | Security Policy: Head of IT and Infrastructure to review security policy within the first 3 months of operations. |  | Head of IT&I | 2024-03-01 | 2024-03-01 | Complete | 100%
A23-01-11 | Amend section related to complaints about CHCs from the complaint’s procedure in April 2024. |  | Governance | 2024-01-01 | 2024-04-01 | Complete | 100%

## Decisions
2024/2025 Llais Board Decisions Tracker
Decision Reference | Decision Items | Date | Status | Overall Status | Notes
D24-12-01 | Audit Report and Accounts: Approved by Board | 2024-12-18 | Approved | Closed
D24-12-02 | Annual Report and letter of representation: Approved by Board | 2024-12-18 | Approved | Closed
D24-09-04 | Corporate Risk Dashboard: An enhanced Dashboard to be produced through the OKR system. | 2024-09-25 | Supported | Open
D24-09-08 | Annual Plan: Approved | 2024-09-25 | Approved | Closed
D24-09-10 | Behaviour Framework: Approved and to be published to the website. | 2024-09-25 | Approved | Closed
D24-07-03 | Standing Orders: The Interim Board Secretary agreed to adjust the document, if required and to submit the endorsed draft standing orders to the Board in July for approval. | 2024-07-24 | Approved | Closed
D24-07-07 | Use of the Common Seal: Supported | 2024-07-24 | Supported | Closed
D24-07-09 | Volunteer Strategy: Approved | 2024-07-24 | Approved | Closed
D24-07-10 | Approved Standing Orders: It was agreed that the standing orders would be posted to the Llais website and that awareness raising with staff would be undertaken to develop understanding and compliance. | 2024-07-24 | Approved | Closed
D24-07-11 | Approved Schedule of Matters Reserved: It was agreed that the schedule of matters reserved would be posted to the Llais website. | 2024-07-24 | Approved | Closed
D24-07-12a | Audit, Risk and Assurance Committee Terms of Reference: Approved | 2024-07-24 | Approved | Closed
D24-07-12b | Workforce, Remuneration and Terms of Service Committee Terms of Reference: Approved | 2024-07-24 | Approved | Closed
D24-07-14 | Communications Strategy: | 2024-07-24 | Approved | Closed
D24-07-15 | Gender Pay Gap: | 2024-07-24 | Supported | Closed
| Draft Financial plan 2024/2025 | 2024-07-24
D24-07-18 | Standing Financial Instructions: The Finance Governance Adviser and the Strategic Director of Operations and Corporate Services agreed to amend the documents, as required, and resubmit them to the committee for approval prior to their submission to the Board in July for approval. | 2024-07-24 | Approved | Closed
D24-04-03 | Corporate Risk: The Board agreed that a new dashboard style Corporate Risk Report/Register would be developed and presented at the July 2024 Board. | 2024-04-24 | Supported | Closed