## Action Log
2025/2026 Llais Board Action Items Tracker
Action Reference | Goals & Action Items | Region Responsible | Person(s) Responsible | Start Date | Due Date | Status | % completion of each action item | Update / Notes
A25-09-01 | Latest sepsis position Further updates would be brought forward to the Board as the new arrangements progressed regarding the latest sepsis position and an update on the development on the call for concern system in Wales. | National Team | Alyson Thomas | 2025-09-24 | 2026-03-26 | In Progress | 75% | Roxanne Treacy to provide a verbal update at the March 2026 Board meeting.
A25-09-02 | The issues of impact - Development Session The Strategic Director of Organisational Strategy and Engagement to deliver a session dedicated to the issues of impact in an upcoming development session. | National Team | Ben Eaton | 2025-09-24 | 2025-11-05 | In Progress | 75% | This theme will be added to the forward work programme for 2026/2027.
A25-09-03 | Working with partners and the third sector update The Aspiring Board Member representative, agreed to provide an update on reflections of working with partners and the third sector, and how to Llais could secure and enhance further relationships. |  | Israa Mohammed | 2025-09-01 | 2025-11-01 | In Progress | 50% | Arrangements are being made to schedule this discussion in the forward work programme for 2026/2027.
A25-07-01 | Spotlight on our activities: Social Care Work with partners to further celebrate success to spread of effective models and the sharing of experiences. | National Team | Ben Eaton | 2025-07-01 | 2026-03-01 | In Progress | 50% | Work has begun on commisioning research into SC celebrating and sharing success - this will be completed in March 2026
A25-07-03 | Spotlight on our activities: Social Care The Chief Executive and Board Secretary to confirm the proposals for the board-to-board session with Social Care Wales. | National Team | Alyson Thomas / Richard Bevan | 2025-07-01 | 2026-01-01 | Complete | 100% | Discussions have taken place with Social Care Wales to agree arrangements. The joint development event took place on Wednesday 25 February 2026.
A25-07-08 | Workforce update including dashboard A series of updates to be submitted to the Workforce, Remuneration and Terms of Service Committee in October 2025. | National Team | Joanne Bolton | 2025-07-01 | 2025-10-01 | Complete | 100% | WRATSC Committee received updates at its meeting on 29 October 2025 for the following: People update report, people strategy (draft), exit interview update and police update report. the Committee was content with the updates. Action completed.
A25-04-01 | To share the people story across Llais to encourage other regions to bring it to the attention of their health and social care partners and HEIW. | West Wales | Donna Coleman | 2025-04-01 | 2025-05-01 | In Progress | 75% | The story has been shared with other regions of Llais as well as further sharing with other social care partners. Specific HEIW discussion has not yet taken place.
A25-11-01 | Develop public statement Produce a clear statement demonstrating Llais' commitment to carers | National Team | Ben Eaton | 2025-11-01 | 2026-05-01 | In Progress | 75% | Llais has developed a response to the Welsh Government's consultation on a national strategy for unpaid carers. Once this is submitted it will be published along with a supporting statement.
A25-11-02 | Future development session Include an update on “what does good engagement look like” in a future Board Development Session. | National Team | Richard Bevan | 2025-11-01 | 2026-06-26 | Complete | 100% | The theme has been added to the forward work programme.
A25-11-03 | Additional action on neurodiversity Report back to the Board at a future meeting on the further work carried out by Llais to address the challenges and concerns of neurodivergent people and their families in health and social care | National Team | Alyson Thomas / Ben Eaton | 2025-11-01 | 2026-05-01 | In Progress | 75% | An update on our further work in this area will be provided at the May 2026 meeting. The next event for neurodivergent children and young people is scheduled in partnershp with the Behaviour Support Hub at the end of March 2026.
A25-11-04 | Agenda for change discussion The Chief Executive to arrange a briefing for the Board on public sector pay arrangements and options | National Team | Alyson Thomas / Executive Team | 2025-11-01 | 2026-06-01 | In Progress | 50% | Briefing preparations are being informed by current discussions at an all Wales level arout pay arrangements across the Welsh public sector.
A25-11-05 | Clinical services proposals Regional Director in West Wales to provide updates on the clinical services proposals. | West Wales | Donna Coleman | 2025-11-01 | 2026-03-01 | In Progress | 50% | Angela Mutlow to provide an update at the March Board meeting.

## Decisions
2025/2026 Llais Board Decisions Tracker
Decision Reference | Decision Items | Date | Status | Overall Status | Notes
D25-05-01 | Voluntary Early Release Scheme Ratification: Ratified by the Board in relation to the Voluntary Early Release Scheme between board meetings on 22 and 23 March 2025. | 2025-05-21 | Approved | Closed
D25-05-02 | Office Moves: Neath Port Talbot and Swansea office move from Cimla to Baglan Bay Innovation Centre - Ratified by the Board | 2025-05-21 | Approved | Closed
D25-05-03 | Common Seal - Cathays Park: Ratified by the Board | 2025-05-21 | Approved | Closed
D25-03-03 | Annual Equality Report: Approved by the Board for publication | 2025-01-26 | Approved | Open
D24-09-04 | Corporate Risk Dashboard: An enhanced Dashboard to be produced through the OKR system. | 2024-09-25 | Supported | Open

## Closed Actions
2025/2026 Llais Board Closed Actions Tracker
Action Reference | Action Items | Region Responsible | Person(s) Responsible | Start Date | Due Date | Status | % completion of each action item | Notes
A24-01-02 | Workforce Metrics: The National Team to provide further information on the diversity of applicants applying for roles within Llais. | National Team | Joanne Bolton/Chris Davies | 2024-01-01 | 2025-05-01 | Complete | 100% | Workforce metrics will be included in reports to the Workforce, Remuneration and Terms of Service Committee and high-level workforce dashboard reports to the Board. Further work is being undertaken with NHS Shared Services Partnership. This will support the extraction and reporting of recruitment data from the Trac system. A further update will be shared at the October WRATS meeting and will form part of the quarterly dashboard reporting. The Board is asked to consider this action closed as it will now be reported to the committee, which did not have its expanded remit when the action was first identified. Assurance reports will be submitted to the Board from the committee as part of routine reporting. The Board agreed to close this in its meeting on 24.09.2025 and move to the completed actions.
A25-07-02 | Spotlight on our activities: Social Care The Chief Executive to engage with the Regional Director of Powys to obtain an update on day centre arrangements in Powys and share this with the Board. | National Team | Alyson Thomas | 2025-07-01 | 2025-09-01 | Complete | 100% | Update received from the Regional Director in Powys. Verbal update to be provided at the September 2025 board meeting.
A25-07-04 | Report from the Chief Executive The Chief Executive to arrange the development of a briefing note on the judicial review process, with legal advice on any implications informing guidance for the staff of Llais. | National Team | Alyson Thomas | 2025-07-01 | 2025-09-01 | Complete | 100% | Legal briefing provided by our legal services and discussed with Executive Team and Audit and Risk Assurance Committee. Advice confirmed the appropriateness of Llais' role in the service change process with no requirement to amend our guidance or approach.
A25-07-05 | Performance against our Annual Plan – Quarter 1 2025/26 The Strategic Director of Organisational Strategy and Engagement to build in further information on impact and ‘The health and social care we want’ programme into future quarterly reports. | National Team | Ben Eaton | 2025-07-01 | 2025-09-30 | Complete | 100% | Board will have a full update on the We Want project as part of the September Board meeting agenda and this is also reflected in the performance update paper.
A25-07-06 | Performance against our Annual Plan – Quarter 1 2025/26 Further briefing would be provided to the Board on ‘The health and social care we want’ programme. This would be incorporated in the Board development programme. | National Team | Ben Eaton / Richard Bevan | 2025-07-01 | 2025-09-01 | Complete | 100% | The theme for the September 2025 Board focuses on the Health and Social Care we want programme. A further update has been added to the forward work programme for the Board. Scheduled for early 2026.
A25-07-07 | Finance report to the end of June 2025 The Strategic Director of Operations and Corporate Services would seek clarification on the national insurance payments for contractors and agency staff. | National Team | Joanne Bolton | 2025-07-01 | 2025-10-01 | Complete | 100% | HMRC is introducing changes for agency staff primarily affecting umbrella companies and recruitment agencies from April 2026, making them jointly liable for unremitted PAYE and National Insurance Contributions (NICs). Our investigation indicates no immediate impact for Llais, as we do not recruit agency staff through umbrella company arrangements. We have also been invited to attend a webinar on 7 October which will provide an update.
A25-07-09 | Board development programme The Board Secretary to submit the new work programme to the Board meeting in September 2025 for approval. | National Team | Richard Bevan | 2025-07-01 | 2025-09-01 | Complete | 100% | An updated forward work programme is on the Board agenda for September 2025 meeting.
A25-07-10 | Questions from the public The position with the final responses to the questions would be confirmed in the action log for the Board to ensure that it became part of the public record. | National Team | Richard Bevan | 2025-07-01 | 2025-09-01 | Complete | 100% | To make sure that the responses given to the two questions submitted to the Board are part of the public record, please find attached an appendix providing an overview of the answers given.
A25-05-02 | The theme of representations to be included in a future scheduled development session. | National Team | Richard Bevan | 2025-05-01 | 2025-09-01 | Complete | 100% | The suggestion has been added to the forward work programme in the second half of the year. This is included within the Board schedule and forward work plan and on the agenda for the meeting on 24 September 2025.
A25-05-03 | Concerns regarding the number of social workers available across local authorities in Wales. Discussions to take place with Social Care Wales | National Team | Alyson Thomas | 2025-05-01 | 2025-06-01 | Complete | 100% | Meeting arranged with Social Care Wales to discuss progress with its Social Work Workforce Plan.
A24-09-04 | Corporate Risk Dashboard: Enhanced Dashboard to be produced through the OKR system. | National Team | Ben Eaton/Richard Bevan | 2024-09-01 | 2025-05-01 | Complete | 100% | A new risk Dashboard has been attached to Board papers in September alongside the new narrative risk report.
A25-04-02 | Letter to be written to Cwm Taf Morgannwg Health Board to highlight the concerns of the Board. Chief Executive to determine the most appropriate approach. | National Team | Alyson Thomas | 2025-04-01 | 2025-05-01 | Complete | 100% | Letter sent 210725 having confirmed that improvement actions are not yet making the difference needed.
A25-05-04 | Llais Events link to be circulated to Board members | National Team | Richard Bevan | 2025-05-01 | 2025-06-01 | Complete | 100%
A25-05-05 | The Interim Board Secretary to finalise a forward work programme and submit it to the Board meeting for approval ay the July 2025 meeting | National Team | Richard Bevan | 2025-05-25 | 2025-07-25 | Complete | 100%
A25-05-01 | Response to be provided regarding question to the Board from a member of the public on the future of stroke services at Bronglais Hospital. | National Team | Richard Bevan / Donna Coleman | 2025-05-01 | 2025-06-01 | Complete | 100%