## Action Log
2026/2027 Llais Board Action Items Tracker
Action Reference | Goals & Action Items | Team Responsible | Person(s) Responsible | Start Date | Due Date | Status | % completion of each action item | Update / Notes
A25-07-01 | Spotlight on our activities: Social Care Work with partners to further celebrate success to spread of effective models and the sharing of experiences. | National Team | Ben Eaton | 2025-07-01 | 2026-03-01 | Complete | 100% | The actions originally identified under the social care spotlight have now been delivered through podcasts, carers engagement activity, the Care at What Cost? programme, partnership working, development of a Social Care Champion role and publication of the forthcoming social care report. The objectives of the Board action have therefore been met and it is recommended that the action is closed, with ongoing social care work reported through routine performance reporting.
A25-04-01 | Patient Story: To share the people story across Llais to encourage other regions to bring it to the attention of their health and social care partners and HEIW. | West Wales | Donna Coleman | 2025-04-01 | 2025-05-01 | In Progress | 75% | The story has been shared with other regions of Llais as well as further sharing with other social care partners. Specific HEIW discussion has not yet taken place.
A25-11-03 | Additional action on neurodiversity Report back to the Board at a future meeting on the further work carried out by Llais to address the challenges and concerns of neurodivergent people and their families in health and social care | National Team | Alyson Thomas / Ben Eaton | 2025-11-01 | 2026-05-01 | In Progress | 75% | Regional work has progressed in this area (referenced in Board papers). A planned all Wales report originally scheduled for Sep has been delayed until later in the year due to capacity.
A25-11-04 | Agenda for change discussion The Chief Executive to arrange a briefing for the Board on public sector pay arrangements and options | National Team | Alyson Thomas / Executive Team | 2025-11-01 | 2026-06-01 | Complete | 100% | Progress is dependent on the policy intentions of the new government on the Welsh public sector. Added to the forward work programmes for the Workforce, Remuneration and Terms of Service Committee forward and the Board and inputs will be organised, when confirmation of the approach is recevied.
A26-03-08 | Scheme of delegation Revise the Chief Executive's scheme of delegation | National Team | Richard Bevan / Alyson Thomas | 2026-03-01 | 2026-06-01 | Complete | 100% | This has been review following Senior Leadership changes and approved changes to the Standing Financial Instructions. This has been finalised and signed off by the Chief Executive and will be forwarded to the Board for information.
A26-03-12 | Forward work programme Populate the 2026/2027 work programme | National Team | Richard Bevan / Karla Lee | 2026-03-01 | 2026-05-01 | In Progress | 75% | The full forward work programme is being discussed and finalised following the approval of four Board meetings a year. Additional discussions required on the sequencing of the town hall and round table events.
A26-05-01 | Declaration of Interest Mair Gwynant to update the Declaration of Interest to reflect a new role on the Board of Natural Resources Wales. | Board | Mair Gwynant | 2026-05-01 | 2026-05-01 | Complete | 100% | Declaration of Interest has been updated.
A26-05-02 | Letter to the First Minister The Chair to write to the First Minister to highlight Llais support where appropriate. | Board | Medwin Hughes | 2026-05-01 | 2026-05-01 | Complete | 100% | Letter sent as planned.
A26-05-03 | Powys Regional Director Presentation Share presenatation with the Board. | Powys Region | Katie Blackburn | 2026-05-01 | 2026-05-01 | Complete | 100% | Presentation made avaiable to Board members.
A26-05-04 | Staff Appraisal Levels It was agreed to further discuss this at the Workforce Renumeration Terms of Service Committee. | National Team | Jason Smith | 2026-05-01 | 2026-10-01 | In Progress | 75% | A further discussion is scheduled for the Committee meeting on the 19 October 2026, as part of the People Report.
A26-05-05 | Board Meeting Schedule for 2026-27 Confirm dates for the forthcoming year. | National Team | Richard Bevan | 2026-05-01 | 2026-05-01 | Complete | 100% | Dates for the 2026/27 and 2027/28 have been confirmed and calendar markers sent out. Please see link to action 26-03-12.

## Completed Actions
2026/2027 Llais Board Action Items Tracker
Action Reference | Goals & Action Items | Region Responsible | Person(s) Responsible | Start Date | Due Date | Status | % completion of each action item | Update / Notes
A25-09-01 | Latest sepsis position Further updates would be brought forward to the Board as the new arrangements progressed regarding the latest sepsis position and an update on the development on the call for concern system in Wales. | National Team | Alyson Thomas | 2025-09-24 | 2026-03-26 | Complete | 100% | It was confirmed in Board in March 2026 that all Health Boards responded appropriately to the representations. Staff training is currently underway, and Llais will continue to ensure that the training was effectively embedded across services, in line with the ongoing action to bring further updates to the Board.
A25-09-02 | The issues of impact - Development Session The Strategic Director of Organisational Strategy and Engagement to deliver a session dedicated to the issues of impact in an upcoming development session. | National Team | Ben Eaton | 2025-09-24 | 2025-11-05 | Complete | 100% | This theme whas been added to 24 June 2026 on the forward work programme but is subject to change once a full programme is finalised.
A25-09-03 | Working with partners and the third sector update The Aspiring Board Member representative, agreed to provide an update on reflections of working with partners and the third sector, and how Llais could secure and enhance further relationships. |  | Israa Mohammed | 2025-09-01 | 2025-11-01 | Complete | 100% | This theme whas been added to 24 June 2026 on the forward work programme but is subject to change once a full programme is finalised.
A25-11-01 | Develop public statement Produce a clear statement demonstrating Llais' commitment to carers | National Team | Ben Eaton | 2025-11-01 | 2026-05-01 | Complete | 100% | We have now published our response to the unpaid carers strategy. The People's Principles reflect the commitment to unpaid carers and will inform all LLais activity in 2026/2027. A national spotlight report on unpaid carers and a report on social care (incorporating matters relating to unpaid carers) have been drafted and will be launched as part of our planned programme now that the pre election period has ended.
A25-11-05 | Clinical services proposals Regional Director in West Wales to provide updates on the clinical services proposals. | West Wales | Donna Coleman | 2025-11-01 | 2026-03-01 | Complete | 100% | The Health Board has now decided a way forward on the 9 change proposals that form its Clinical Services Strategy. Its preferred option on stroke services, which has been developed from feedback on the original consultation will now be subject to further public consultation, and following representations from Llais, the Health Board will now develop a transport strategy in response to the issues raised by people through the consultation and more broadly. Llais continues to make representations to the Health Board around the strategy to inform and influence action in response to what we hear. Further updates will be reported as required through regular reporting arrangements. | The Health Board made its decision on the 9 service change proposals at a public board meeting in February 2026. A final decision has not yet been made on stroke services, as the board's preferred option differs from the oroginal proposals so is subject to further public consultation. Llais continues to monitor and make representations relating to the Clinlcal Services Strategy so that the Health Board responds to the issues raised by people.
A25-03-01 | Declaration of interest Board members to receive their 2024/2025 declarations of interest forms to help with completing the 2025/2026 return. | National Team | Karla Lee | 2026-03-01 | 2026-03-01 | Complete | 100% | Karla sent Board members their 2024/2025 declarations of interest forms on 26 March 2026.
A25-03-02 | Analysis Send analysis of the King’s Fund report to Board members that was previously sent to Directors | National Team | Ben Eaton | 2026-03-01 | 2026-05-01 | Complete | 100% | Report sent to Board members on 23 March 2026
A25-03-03 | Public Statement Issue a public statement at the conclusion of the three-year period | National Team | Medwin Hughes / Ben Eaton | 2026-03-01 | 2026-05-01 | Complete | 100% | Released press statement tied to the Chair's extension.
A25-03-04 | Pre-election guidance The Corporate Director of Governance and Board Secretary to issue the guidance that had been developed once translated into Welsh. | National Team | Richard Bevan | 2026-03-01 | 2026-03-01 | Complete | 100% | Richard sent an email with the pre-election guidance to members on 30 March 2026.
A25-03-05 | Allocate time at a future development session to discuss the Listening to People process, evidence of learning, and how agreed priorities will translate into actions and outcomes. | National Team | Richard Bevan | 2026-03-01 | 2026-05-01 | Complete | 100% | This took place at the Board development session on 29 Aptil 2026.
A25-03-06 | Internal framework Develop an internal framework to test and evaluate programmes and policy proposals against the People’s Principles. | National Team | Ben Eaton | 2026-03-01 | 2027-04-01 | Complete | 100% | Work has started on the internal developemtn programme - we are yet to appoint to the programme manager role, Board will be updated regularly as part of performance reporting - this will feature as a major part of the programme
A25-03-07 | Access issues Contact the Regional Directors to review access issues and to specifically link with the Regional Director in Gwent | National Team | Ben Eaton | 2026-03-01 | 2026-05-01 | Complete | 100% | All RDs have been asked to review communication access standards as part of the engagement plans, and reviews of LTP complaints, there is also complementary work ongoing through our SEP programme re communication with different communities.
A25-03-09 | Workforce, Remuneration and Terms of Service Committee briefing Circulate briefing to members. | National Team | Richard Bevan / Karla Lee | 2026-03-01 | 2026-05-01 | Complete | 100% | This has been included within the WRATS report and added to the agenda.
A25-03-10 | Ambassador role Review the ambassador role and bring a report to the Development Session in April 2026 | National Team | Richard Bevan | 2026-03-01 | 2026-04-01 | Complete | 100% | A Forms questionnaire has been developed and sent out to members to help form the review. An analysis has been done and discussed in the Development session on 29 April 2026.
A25-03-11 | Board invites Send out new invites for the confirmed Board dates | National Team | Karla Lee | 2026-03-01 | 2026-03-01 | Complete | 100% | New invites were sent on 10 April 2026 for the confirmed Board meetings and updated the original invites to be placeholders until a full work programme has been finalised.

## Decisions
2025/2026 Llais Board Decisions Tracker
Decision Reference | Decision Items | Date | Status | Overall Status | Notes
D25-05-01 | Voluntary Early Release Scheme Ratification: Ratified by the Board in relation to the Voluntary Early Release Scheme between board meetings on 22 and 23 March 2025. | 2025-05-21 | Approved | Closed
D25-05-02 | Office Moves: Neath Port Talbot and Swansea office move from Cimla to Baglan Bay Innovation Centre - Ratified by the Board | 2025-05-21 | Approved | Closed
D25-05-03 | Common Seal - Cathays Park: Ratified by the Board | 2025-05-21 | Approved | Closed
D25-03-03 | Annual Equality Report: Approved by the Board for publication | 2025-01-26 | Approved | Open
D24-09-04 | Corporate Risk Dashboard: An enhanced Dashboard to be produced through the OKR system. | 2024-09-25 | Supported | Open

## Closed Actions
2026/2027 Llais Board Closed Actions Tracker
Action Reference | Action Items | Region Responsible | Person(s) Responsible | Start Date | Due Date | Status | % completion of each action item | Notes
A25-07-03 | Spotlight on our activities: Social Care The Chief Executive and Board Secretary to confirm the proposals for the board-to-board session with Social Care Wales. | National Team | Alyson Thomas / Richard Bevan | 2025-07-01 | 2026-01-01 | Complete | 100% | Discussions have taken place with Social Care Wales to agree arrangements. The joint development event took place on Wednesday 25 February 2026.
A25-07-08 | Workforce update including dashboard A series of updates to be submitted to the Workforce, Remuneration and Terms of Service Committee in October 2025. | National Team | Joanne Bolton | 2025-07-01 | 2025-10-01 | Complete | 100% | WRATSC Committee received updates at its meeting on 29 October 2025 for the following: People update report, people strategy (draft), exit interview update and police update report. the Committee was content with the updates. Action completed.
A25-11-02 | Future development session Include an update on “what does good engagement look like” in a future Board Development Session. | National Team | Richard Bevan | 2025-11-01 | 2026-06-26 | Complete | 100% | The theme has been added to the forward work programme.